## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | I want a synthetic data generation script for 3k+ emails | Must Have | - | Samith S | 3- Completed
Sprint 1 | Sprint 1 | US-02 | I want an NLP preprocessing script using NLTK | Must Have | US-01 | Samith S | 3- Completed
Sprint 2 | Sprint 2 | US-03 | I want a TF-IDF vectorizer + XGBoost for category classification | Must Have | US-02 | Samith S | 3- Completed
Sprint 2 | Sprint 2 | US-04 | I want a Logistic Regression model for urgency detection | Must Have | US-02 | Samith S | 3- Completed
Sprint 3 | Sprint 3 | US-05 | I want a custom dataset parser to train on 204k actual emails | Should Have | US-03 | Samith S | 3- Completed
Sprint 4 | Sprint 4 | US-06 | I want a Streamlit web interface with analysis capabilities | Must Have | US-04 | Samith S | 3- Completed
Sprint 4 | Sprint 4 | US-07 | I want a Dashboard with KPI cards and interactive Plotly charts | Must Have | US-06 | Samith S | 3- Completed

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 3 | Missing NLTK corpora breaking text cleaner | Added dynamic installer to init
Sprint 2 | Day 10 | PyTorch environment throwing complex DLL errors | Migrated to robust Scikit-Learn/XGBoost approach
Sprint 3 | Day 20 | Labels in 204k dataset grouping to 3 instead of 5 | Rewrote custom dataset processor to preserve original labels
Sprint 4 | Day 30 | Streamlit widget key conflict on dashboard button | Implemented pending flag pattern via session_state

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-02-01 | 2026-02-07 | Samith S | Focusing on clean NLP processing | Using PyTorch for simple text | Writing functional tests | Preprocess complete
2 | Sprint 2 | 2026-02-01 | 2026-02-07 | Samith S | Rethinking tech stack constraints | Assuming DLLs work cross platform | Documenting architectures | Models trained (98% acc)
3 | Sprint 3 | 2026-02-01 | 2026-02-07 | Samith S | Scaling dataset logic | Assuming label structures | Preserving dataset balance | 204k Custom dataset parsed
4 | Sprint 4 | 2026-02-01 | 2026-02-07 | Samith S | Debugging Streamlit flows | Nesting state changes | Iterating quickly on UI | Dashboard live and verified